## Project Timeline
CareWheels - Timeline |  |  |  | 2016
|  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUG |  |  |  | SEPT
Deliverables |  | Owner | Duration | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Planning phase |  |  | 2 w
| Gather MVP Requirements |  | 2 w
| Team acceptance of Requirements |  | 2 w
| Sponsor acceptance of requirements |  | 2 w
| Process use cases |  | 2 w
| Search for missing use cases |  | 2 w
| Research Cyclos and Sen.se APIs |  | 2 w
| Research Mobile SDK Options |  | 2 w
| Define non-functional requirements |  | 2 w
| Risk Collection |  | 2 w
| Risk Mitigation Plans |  | 2 w
| Assign Roles |  | 2 w
| Git Repo |  | 2 w
| Backup Plan |  | 2 w
| Work Breakdown Schedule |  | 2 w
| Timeline Document |  | 2 w
Team phase |  |  | 2 w
| Architectural Design |  | 2 w
| Pseudocode Development |  | 2 w
1 w
Prototype phase |  |  | 2 w
| Ionic Prototype |  | 2 w
| Sen.se Rest API Prototyping |  | 3 w
| Solve port forwarding/team access |  | 2 w
2 w
2 w
Implementation phase |  |  | 5 w
| Populate Group Spokes |  | 5 w
| Display Login and Password fields and submit button |  | 5 w
| Write JavaScript UI |  | 3 w
| Write Java cyclos client code to log user into cyclos |  | 3 w
| Display Save Credentials checkbox |  | 5 w
| Write method to save username and password to local storage when box is checked. |  | 3 w
| Display Hub |  | 5 w
| User Photo |  | 3 w
| Query field in cyclos |  | 2 w
| Render hub photo |  | 2 w
| User's Name |  | 3 w
| Query field in cyclos |  | 2 w
| Render hub photo |  | 2 w
| Display each spoke |  | 5 w
| Display name |  | 3 w
| Query field in cyclos |  | 2 w
| Render spoke name |  | 2 w
| Spoke alerts |  | 3 w
| Get state of each spoke |  | 2 w
| Display colors representing current state of spoke. |  | 2 w
| Spoke photo (stretch) |  | 3 w
| Query field in cyclos |  | 2 w
| Render hub photo |  | 2 w
| Display user account balance |  | 3 w
| Query Cyclos endpoint for user account balance |  | 2 w
| Render balance information |  | 2 w
| Credit user for time spent on this screen |  | 3 w
| Write Javascript to calculate time spent on page and credits to deliver. |  | 2 w
| Use cyclos REST endpoint to update balance |  | 2 w
| Display spoke graphs/sensor info |  | 3 w
| Display call button |  | 3 w
| Enable call functionality with Cordova plugin |  | 2 w
| Credit user for time spent on this screen |  | 3 w
| Track active time spent on screen. |  | 2 w
| Use cyclos REST endpoint |  | 2 w
| Credit user for time spent on call |  | 3 w
| Use cyclos REST endpoint |  | 2 w
| Check call log to retrieve duration info |  | 2 w
| Cyclos Server group setup |  | 5 w
| Perform manual group creation and user assignment to group. |  | 2 w
| Cyclos server user alert status |  | 3 w
| Create custom user field to store a clients fridge sensor alert status. |  | 2 w
| Confirm that *presence* sensor data can be collected/stored |  | 2 w
| Confirm that *presence* sensor data can be accessed |  | 2 w
| Define method which takes *presence* sensor data as input and returns a color state |  | 3 w
| Define blue state dependencies for *presence* sensor |  | 2 w
| Define red state dependencies for *presence* sensor |  | 2 w
| Define yellow state dependencies for *presence* sensor |  | 2 w
| Define green state dependencies for *presence* sensor |  | 2 w
| Confirm that *door* sensor data can be collected/stored |  | 2 w
| Confirm that *door* sensor data can be accessed |  | 2 w
| Define method which takes *door* sensor data as input and returns a color state |  | 3 w
| Define blue state dependencies for *door* sensor |  | 2 w
| Define red state dependencies for *door* sensor |  | 2 w
| Define yellow state dependencies for *door* sensor |  | 2 w
| Define green state dependencies for *door* sensor |  | 2 w
| Confirm that *meds* sensor data can be collected/stored |  | 2 w
| Confirm that *meds* sensor data can be accessed |  | 2 w
| Define method which takes *meds* sensor data as input and returns a color state |  | 3 w
| Define blue state dependencies for *meds* sensor |  | 2 w
| Define red state dependencies for *meds* sensor |  | 2 w
| Define yellow state dependencies for *meds* sensor |  | 2 w
| Define green state dependencies for *meds* sensor |  | 2 w
Closure phase |  |  | 6 w
Test Server Functionality
Test Sensor Functionaly
Test App Functionality
Deliver software and documentation to sponsor
Annotations