## Risks
Project |  |  | CareWheels | [5 empty] | Project #
Project manager | [8 empty] | Sponsor
Updated
ID | Risk Description | Probability | Severity | Risk | Category | Trigger Event/Indicator | Risk Response and Description | Contingency Plan | Owner | Status | Date Entered | Date to Review
[6 empty] | What act or event initiates either the risk occurrence or precipitates the response strategy? | How will you respond to this risk and what actions will you take to match that response? | If the risk becomes a reality, what will you do in response, as a backup, or alternative/ workaround? | Who monitors this risk?
1 | Requirements for interfacing with other systems, other complex systems, or other systems that are not under the team’s control result in unforeseen design, implementation, and testing | 4 | 4 | 16 | Product | Reports show that many failures were not caused by the team's product. | Mitigation. The Project Manager will need to have a discussion with the team to understand what happened. Also, he also need to have another discussion with the customer to update the requirements if necessary. | After necessary meeting, the team will need to implement a workaround for this issue. | Project Manager | Open | 2016-05-10
2 | Inaccurate progress tracking results in not knowing the project is behind schedule until late in the project | 4 | 4 | 16 | Process | The schedule lead notify the manager that the team will not meet the deadline. | Avoidance. The project manager needs to communicate with the team regularly and make any changes if neccessary. | Regular team meeting will take place. Under some circumstances, another team meeting will take place to solve specific issues. | Project Manager | Open | 2016-05-10
3 | Inaccurate quality tracking results in not knowing about quality problems that affect the schedule until late in the project | 4 | 4 | 16 | Process | Product could not meet expected quality after many testing cycles. | Avoidance. The project manager needs to communicate with schedule lead and requirement lead regularly and make any changes if neccessary. | The team schedule and/or the requirents document will be updated regularly. Extra working time might be required. | Project Manager | Open | 2016-05-10
4 | Error-prone modules require more testing, design, and implementation work than expected | 4 | 3 | 12 | Product | Reports show that many failures has not been fixed. | Mitigation. The Project Manager will need to have a discussion with the team to understand what happened and change the testing plan if possible. | After necessary meeting, the team will need to implement a workaround for this issue. | Project Manager | Open | 2016-05-10
5 | Development tools do not work as expected; developers need time to create workarounds or to switch to new tools | 3 | 3 | 9 | Development | Development is slowed because of development tool issues. | Avoidance. As much testing as can be done before hand will be done. | Workarounds or new tools will be explored. | IT Infrastructure Lead | Open | 2016-05-10
6 | Personnel need extra time to learn unfamiliar software tools or environment | 3 | 3 | 9 | Team Member | The team member's progress is slow. | Mitigation. A discussion between the team member and project manager will take place to find out what work best for the team. | Project Manager will need to provide the team member some training or some extra time until he finishes learning. | Project Manager | Open | 2016-05-10
7 | Overly complicated design requires unnecessary and unproductive implementation overhead | 3 | 3 | 9 | Implementation | Some components take a lot of time to implement and block another tasks. | Avoidance. When at the requirement analisys phase, the team should spend extra time to discuss about the design carefully. | There will be many meetings between the customer and the team to find the best solution. | Project Manager | Open | 2016-05-10
8 | Code or class libraries have poor quality, causing extra testing, defect correction, and rework | 3 | 3 | 9 | Implementation | Test reports show many failures. | Mitigation. A discussion between project manager and developers will take place in order to improve the product quality and performace and prevent it from happening again. | The development team might need to spend extra time to improve the impletation progress. | Project Manager | Open | 2016-05-10
9 | Amount of paperwork results in slower progress than expected | 3 | 3 | 9 | Process | The Archivist/Secretary wants to get help in documents. | Avoidance. The Archivist/Secretary need to discuss with the team to find a way to organize and finish the paperwork. | The IT Infrastructure Lead and Project Manager need to assist the Archivist/Secretary on the paperwork progress in order to complete it as soon as possible. | Project Manager | Open | 2016-05-10
10 | Schedule is too optimistic | 2 | 4 | 8 | Schedule | The Team starts to fall behind the schedule. | Mitigation. A discussion will take place as to why the Team is missing deadlines, and corrections to the problem will be found. | Schedule revisions will take place. | Schedule Lead | Open | 2016-05-10
11 | Operation in an unfamiliar or unproved environment causes unforeseen problems | 2 | 4 | 8 | Product | An unexpected issue happens. | Avoidance. When at the requirement analisys phase, the team should spend extra time to discuss about the design carefully. | The team will need to spend extra time to analyze and fix those problems. | Project Manager | Open | 2016-05-10
12 | Components developed separately cannot be integrated easily, requiring redesign and rework | 2 | 4 | 8 | Implementation | Reports from developers show that extra work will be needed. | Mitigation. A discussion between project manager and developers will take place in order to discuss the affect on the project. | A new plan for the project will be announced. | Project Manager | Open | 2016-05-10
13 | Cannot build a product of the size specified in the time allocated | 2 | 3 | 6 | Schedule | Deadlines are continually being missed. | Avoidance. A realistic MVP needs to be in place. | Revisions to the MVP would be needed, or changes become priority after MVP is completed. | Project Manager | Open | 2016-05-10
14 | Effort is greater than estimated | 3 | 2 | 6 | Schedule | Deadlines are continually being missed. | Avoidance. Testing should be done before-hand, and accurate assessment of skills should be gathered. | The team needs to ask for help when it is needed. The schedule may need adjustments. | Schedule Lead | Open | 2016-05-10
15 | Customer insists on new requirements | 3 | 2 | 6 | Customer | Sponsor adds to the MVP. | Avoidance. The MVP will be agreed upon by all parties beforehand. | Additions will be looked at to see if they are viable. | Requirement Lead | Open | 2016-05-10
16 | Customer review/decision cycles for plans, prototypes, and specifications are slower than expected | 3 | 2 | 6 | Customer | A key piece of information is missing making it difficult to complete a task. | Avoidance. Correspondance will continually take place to try to minize this. | The team will work on tasks that can be completed while waiting for the information. | Sponsor Second Contact | Open | 2016-05-10
17 | Requirements have been baselined but continue to change | 2 | 3 | 6 | Requirement | Deadlines are continually being missed. | Avoidance. A realistic MVP needs to be in place. | Revisions to the MVP would be needed, or changes become priority after MVP is completed. | Requirement Lead | Open | 2016-05-10
18 | Requirements are poorly defined, and further definition expands the scope of the project | 2 | 3 | 6 | Requirement | Development is slowed because discussion about the requirements is unclear. | Avoidance. The Req Spec will be procise. | The Req Spec will be made more clear. | Requirement Lead | Open | 2016-05-10
19 | People’s assignments do not match their strengths | 3 | 2 | 6 | Team Member | A team member request to change his assignment. | Mitigation. A discussion between the team member and project manager will take place to find out what work best for the team. | Team member will find a better way to improve his performance. | Project Manager | Open | 2016-05-10
20 | Sponsor disappears | 1 | 4 | 4 | Management | No contact from Claude or Bill | Acceptance. Project Manager will try to make contact and alert Bart to the situation. | The team will continue with the specifications that we have in place. | Project Manager | Open | 2016-05-08
21 | Target date is moved up with no corresponding adjustment to the product scope or available resources | 1 | 4 | 4 | Schedule | Sponsor or Bart tells us that the finish date is moved up. | Acceptance. Tasks are increased as needed. | The team will do the best that it can with the time allotted. | Schedule Lead | Open | 2016-05-10
22 | A delay in one task causes cascading delays in dependent tasks | 4 | 1 | 4 | Schedule | A critical element is missing. | Avoidance. Everyone will communicate progress, and help will be assigned if needed. | A group effort will smooth out any delays. A revision to the schedule may be needed. | Schedule Lead | Open | 2016-05-10
23 | Inefficient team structure reduces productivity | 2 | 2 | 4 | Management | Deadlines are being missed. | Avoidance. Project Manager will assign tasks to people who say they can handle them. | Roles will be reassigned. | Project Manager | Open | 2016-05-10
24 | Management review/decision cycle is slower than expected | 2 | 2 | 4 | Management | A key piece of information is missing making it difficult to complete a task. | Avoidance. Correspondance will continually take place to try to minize this. | The team will work on tasks that can be completed while waiting for the information. | Project Manager | Open | 2016-05-10
25 | Nontechnical third-party tasks take longer than expected | 1 | 4 | 4 | Management | Something like a license means that our project become unaviable. | Acceptance. Everyone does what they can to work around this. | Depending on when this takes place, the team can make adjustments as needed. | Project Manager | Open | 2016-05-10
26 | Development tools are not in place by the desired time | 2 | 2 | 4 | Development | Deadline for development tools is missed. | Avoidance. The IT Lead should communicate problems. | The Team will help the IT Lead as needed. | IT Infrastructure Lead | Open | 2016-05-10
27 | Customer micro-manages the development process, resulting in slower progress than planned | 2 | 2 | 4 | Customer | Sponsor tells the Project Manager how to run the project. | Avoidance. Boundaries were set in place before hand, so this should not be an issue. | Communication with the Sponsor should make the Sponsor feel like their opinions are validated. | Sponsor Second Contact | Open | 2016-05-10
28 | Development of extra software functions that are not required extends the schedule | 2 | 2 | 4 | Product | The developers work on low piority tasks which not required. | Mitigation. Sometimes implementing extra feature would benefit the overall development. A meeting with project manager is required before doing that. | A plan to implement extra feature will announce and should not take a lot of time. | Project Manager | Open | 2016-05-10
29 | Necessary functionality cannot be implemented using the selected code or class libraries; developers must switch to new libraries or custom-build the necessary functionality | 1 | 4 | 4 | Implementation | After some testing, the product still do not have enough features as expected. | Mitigation. A discussion between project manager and developers will take place in order to improve the product quality and performace and prevent it from happening again. | The development team might need to spend extra time to improve the impletation progress. The team schedule will be updated. | Project Manager | Open | 2016-05-10
30 | Remote code repository fails. General loss of work and history of development. | 1 | 4 | 4 | Implementation | GitHub fails and remote repository gets deleted. | Mitigation. Restore remote repository using github snapshots. | Snapshots of the remote github repository will be taken routinely. | Backup Manager | Open | 2016-05-12
31 | Schedule omits necessary tasks | 1 | 3 | 3 | Schedule | Sponsor or Team Member notices that element is missing. | Mitigation. As soon as the element is identified, the Schedule Lead will assign tasks to get it done. | Schedule revisions will take place. | Schedule Lead | Open | 2016-05-10
32 | Management makes decisions that reduce the development team’s motivation | 3 | 1 | 3 | Management | A Team Member seems disconnected. | Avoidance. The Team will keep an eye on eachother, and we will communicate effectively. | The Project Manager will make decisions that individuals don't like. Accept that the job is hard and communicate your feelings. | Project Manager | Open | 2016-05-10
33 | Facilities are not available on time | 3 | 1 | 3 | Development | Something equivalent to a meeting of another group going into our time for the space. | Acceptance. We will use different facilities/times if needed. | Move the location or time. | Project Manager | Open | 2016-05-10
34 | Development tools are not chosen based on their technical merits, and do not provide the planned productivity | 1 | 3 | 3 | Development | A disagreement about a development tool is exposed. | Avoidance. Discussion and voting can be done for development tools that don't need to be specifically used. | Workarounds or new tools will be explored. | IT Infrastructure Lead | Open | 2016-05-10
35 | Customer will not participate in review cycles for plans, prototypes, and specifications or is incapable of doing so - resulting in unstable requirements and time consuming changes | 1 | 3 | 3 | Customer | Something like not getting sensor data takes place. | Avoidance. Correspondance will continually take place to try to minize this. | The team will work on tasks that can be completed while waiting for the information, or a workaround will be used. | Sponsor Second Contact | Open | 2016-05-10
36 | Development of the wrong software functions requires redesign and implementation | 1 | 3 | 3 | Product | The developer report that this software function is not needed. | Mitigation. A meeting will be take place to discuss about the affect and prevent it happening again. | The developer might need to rush to keep up with the project. | Project Manager | Open | 2016-05-10
37 | Meeting product’s size or speed constraints requires more time than expected, including time for redesign and reimplementation | 1 | 3 | 3 | Product | The developers could not move on without solving some constraints. | Mitigation. A discussion between project manager and developers will take place in order to discuss the affect on the project. | Depending on the discussion, a new plan will be announced. | Project Manager | Open | 2016-05-10
38 | Strict requirements for compatibility with existing system require more testing, design, and implementation than expected | 1 | 3 | 3 | Product | Product implementation, design, and testing take too long to finish. | Acceptance. Product quality is high priority. The project manager should discuss with customer to update the schedule. | After discuss with the customer, the team will have a new plan for those requirements. | Project Manager | Open | 2016-05-10
39 | Team members do not work together efficiently | 3 | 1 | 3 | Team Member | Some of the team members are not up to date. | Mitigation. A discussion between each team member and project manager will take place to find out what work best for the team and resolve conflict. | Project Manager will need to encourage teamwork to maximize the team's performance. | Project Manager | Open | 2016-05-10
40 | Software project risk management takes more time than expected | 3 | 1 | 3 | Process | Project Manager has not got any update from the risk management process. | Avoidance. Risk Management Lead will ask other team members for helps. | One or more team members will working on the document together to finish it as soon as possible. | Project Manager | Open | 2016-05-10
41 | Schedule was based on the use of specific team members, but those team members were not available | 1 | 2 | 2 | Schedule | No contact from a Team Menber | Mitigation. Project Manager will try to make contact. If Project Manager disappears, a new Project Manager is chosen and that person will try to make contact. | Schedule Lead assigns Team Members the specific tasks. | Schedule Lead | Open | 2016-05-10
42 | Team members do not buy into the project and consequently does not provide the level of performance needed | 1 | 2 | 2 | Team Member | A team member out of the from the project. | Mitigation. A discussion between team member and project manager will take place to find out what work best for the team and resolve conflict. | Project Manager will need to improve the team communication to keep everyone up to date. | Project Manager | Open | 2016-05-10
43 | Management-level progress reporting takes more developer time than expected | 2 | 1 | 2 | Process | Reports from developers show slower performance than expected. | Mitigation. A discussion between project manager and developers will take place in order to improve current reporting progress. | The reporting progress or the developers schedule will be updated. | Project Manager | Open | 2016-05-10