## Sheet1
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7
CareWheels Project
Planning Phase
Requirements
MVP Definition
MVP Requirements Gathering
Team Acceptance
Sponsor Acceptance/Revision
Define Stakeholders
Use Cases
Process provided use cases
Search for missing use cases
Functional Requirements
Research Cyclos and Sen.se APIs
Research Mobile SDK Options
Non Functional Requirements
Risk Management
Risk Management Document
Risk Collection
Risk Mitigation Plans
Infrastructure
Assign Roles
Git Repo
Backup Plan
Scheduling
Work Breakdown Schedule
Timeline Document
Team Phase
Design
Architectural Design
Psuedocode Development
Prototype Phase
Front-end
Ionic Prototype
This should be broken up into several subtasks
Sen.se Rest API Prototyping
This should be broken up into several subtasks
Back-end
Cyclos server
Solve port forwarding/team access
Implementation Phase
Mobile App
|  |  | Navigation menu | (Menu is for development of future screens and to allow people to easily go back to the spoke selection screen)
Display button to navigate to Spoke selection screen
Login screen
Display Login and Password fields and submit button
Write JavaScript UI
Write Java cyclos client code to log user into cyclos
Display Save Credentials checkbox
Write method to save username and password to local storage when box is checked.
Spoke selection screen
Display Hub
User Photo
Query field in cyclos
Render hub photo
User's Name
Query field in cyclos
Render hub name
Display each spoke
Display name
Query field in cyclos
Render spoke name
Spoke alerts
Get state of each spoke
Display colors representing current state of spoke.
Spoke photo
Query field in cyclos
Render spoke photo
Display user account balance
Query Cyclos endpoint for user account balance
Render balance information
Credit user for time spent on this screen
Write Javascript to calculate time spent on page and credits to deliver.
Use cyclos REST endpoint to update balance
Single spoke detail screen
Display spoke graphs/sensor info
Query Cyclos for stored sensor data (3 sensors)
Display call button
Enable call functionality with Cordova plugin
Credit user for time spent on this screen
Track active time spent on screen.
Use cyclos REST endpoint
Credit user for time spent on call
Use cyclos REST endpoint
Check call log to retrieve duration info
Cyclos Server
Group setup
Perform manual group creation and user assignment to group.
User alert status
Create custom user field to store a clients fridge sensor alert status.
3 Sensor Test Design
Presence Detection
Confirm that sensor data can be collected/stored
Confirm that sensor data can be accessed
Define method which takes sensor data as input and returns a color state
Blue state dependencies
Return blue state if application is off
Return blue state if user is away from residence as determined by sensor
Red state dependencies
If yellow alert has been promoted to red by duration
Yellow state dependencies
If Sen.se alert generated or refrigerator indicates missed meal
Green state dependencies
Activity has been detected; no alerts
Movement Detection (door)
Confirm that sensor data can be collected/stored
Confirm that sensor data can be accessed
Define method which takes sensor data as input and returns a color state
Blue state dependencies
Red state dependencies
Presence == true && no door activity for y hours
Immediately return red state (door)
Yellow state dependencies
Presence == true && no door activity for x hours
Immediately return yellow state (door)
Green state dependencies
Presence is detected && door activity has occured within normal span
Meds Taken On Time
Confirm that sensor data can be collected/stored
Confirm that sensor data can be accessed
Define method which takes sensor data as input and returns a color state
Blue state dependencies
Red state dependencies
Presence == true && Data shows inactivity of more than y minutes
Immediately return red state (meds)
Yellow state dependencies
Presence == true && Data shows inactivity of more than x minutes
Immediately return yellow state (meds)
Green state dependencies
Activity is detected within x minutes
Closure Phase
Testing
Server Functionality
Sensor Functionaly
App Functionality
Front-End
Back-End
Deployment
Deliver software and documentation to sponsor